## Slide 1
Agile Delivery Operating Model
A predictable, transparent way of building software — two-week sprints, a single Jira source of truth, and ceremonies that connect daily work to quarterly OKRs.
2-Week Sprints · Mon → Fri
Jira-Driven Workflow
OKR-Aligned Epics
Quarterly PI Planning
Outcome
alignment
Every Epic ladders up to a quarterly OKR. Leadership sees why work happens, not just what.
Predictability
Velocity & capacity planning turn estimates into reliable, forecastable delivery dates.
Transparency
A live Jira board means real-time status — no status-chasing, no deadline surprises.
Continuous improvement
Retros convert problems into actions every two weeks, so the team gets measurably faster.
Why we are moving to this model
Not 'more process' — predictable delivery, early visibility of risk, and a clear line from effort to business outcomes.

## Slide 2
THE SPRINT > 2-Week Heartbeat
Sprints run Monday of Week 1 → Friday of Week 2 — 10 working days. A fixed rhythm makes velocity meaningful and planning trustworthy.
Sprint Goal - Every sprint has one sentence describing the outcome it delivers. It keeps scope of success beyond a checklist of tickets.
10
working days
per sprint
26
sprints in
a year
~6
sprints per
quarter / PI
JIRA WORKFLOW
Five states. Tickets move left → right. WIP limits keep the team finishing work before starting new work.
READY TO START
IN PROGRESS
DEV COMPLETE
TEST COMPLETE
DONE
WIP
Limit work in progress
Cap each column. Less in progress = more finished. Bottlenecks show instantly.
DEV → TEST
Quality is built in
'Dev Complete' ≠ Done. QA verification is a first-class column.
DONE
Done means Done
A ticket only reaches Done when it meets the Definition of Done.

## Slide 3
THE MODEL — ONE VIEW
From strategy to daily delivery, at a glance
1
FOUR ALTITUDES
YEARLY Strategy & roadmap — Leads own product themes
QUARTERLY · PI OKRs & Program Increment planning → Epics
BI-WEEKLY · SPRINT Planning → Review → Retro; Epics → Stories
DAILY 15-min standup — sync, blockers, re-plan
2
JIRA HIERARCHY
OKR Reduce order-handling time 40%
EPIC AI-first WhatsApp order flow
STORY Place an order via chat intent
SUB-TASK Wire classifier → order service
Each ticket tagged with Fix Versions · Components · Quarter / PI field
3
CEREMONIES
Daily Standup
15m · daily
Backlog Grooming
60m · /sprint
Sprint Planning
90m · Day 1
Review / Demo
45m · last day
Retrospective
45m · last day
PI Planning
½ day · quarterly
OKR Discussion
quarterly + check
Every ceremony is timeboxed — meetings enable building, not replace it.
4
SPRINT CADENCE · 2 WEEKS
WEEK 1
MON
Planning
TUE
build
WED
build
THU
Grooming
FRI
build
WEEK 2
MON
build
TUE
build
WED
build
THU
Code freeze
FRI
Demo + Retro
Daily standup every working day. Quarter opens with PI Planning + OKR review.

## Slide 4
PLANNING · SPRINT MECHANICS
Capacity, velocity & burndown
Capacity = Members × Sprint Days × Focus Factor − (Leave + Holidays + Ceremony time)
Worked example — 5-person team
Team members
5
Working days / sprint
10
Gross person-days
50
Focus factor (~75%)
× 0.75
Planned leave
− 3 days
Net capacity
≈ 34.5 p-days
Focus factor 0.7–0.8 reserves time for review, meetings & support — so commitments stay honest.
Velocity trend
story points / sprint
Chart: 
| S10 | S11 | S12 | S13 | S14
Velocity | 27 | 31 | 36 | 33 | 38
Sprint burndown
points remaining
Chart: 
| D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Ideal | 42 | 37.3 | 32.7 | 28 | 23.3 | 18.7 | 14 | 9.3 | 4.7 | 0
Actual | 42 | 41 | 40 | 33 | 31 | 26 | 21 | 22 | 14 | 3
Capacity → commitment: convert net capacity into a story-point target using recent velocity. Last sprint (S14): ~42 committed → 40 completed → 95% predictable.

## Slide 5
HOW WE WORK & MEASURE
Roles, quality gates & metrics
1
ROLES & OWNERSHIP
Product Owner
The 'what' & priority; backlog & OKR alignment
Scrum Master
Process & flow; removes blockers
Tech Lead
Architecture, roadmap & technical risk
Developers
The 'how' — build & self-organise
QA / Test
Quality gates: Dev Complete → Done
Leadership
Strategy, OKRs, org-level unblocking
2
QUALITY GATES
Definition of Ready
Clear, testable acceptance criteria
Estimated in story points
Dependencies identified & resolvable
Designs / API contracts attached
Fits within one sprint
Definition of Done
Code reviewed & merged
Unit + integration tests pass
QA verified vs. criteria
Docs / changelog updated
Deployed to staging, demo-ready
3
METRICS WE WATCH
Velocity stability
Low variance, not heroics
Sprint predictability
80–90% of commitment delivered
Cycle time
In Progress → Done (shorter = better)
Spillover rate
Carried work trending down
Escaped defects
Bugs found after Done
OKR progress
Key-result movement / quarter

## Slide 6
GETTING THERE
Rollout plan
We don't flip a switch — we ramp into the rhythm over the first month.
W1
Set up Jira & train the team
Configure board states, issue types, fix versions & OKR/quarter fields. Walk the workflow together.
W1
Define the working agreements
Agree the Definition of Ready, Definition of Done, WIP limits, and ceremony times as a team.
W2
Backlog & first PI plan
Prepare Epics from current OKRs, groom the backlog top, run the first PI planning session.
W3
Run Sprint 1
Plan conservatively, hold daily standups, complete the first full sprint cycle.
W4
First retro & calibrate
Establish baseline velocity, review what worked, lock in the cadence going forward.